## Add Work Zone
Name | Description | IMPACT
SP# 0214-41 | Bit Mill and Overlay, Guardrail, etc. | HI
SP# 0280-61 | Bit Mill and Overlay, Deck Repair, Traffic Barrier, etc. | HI
SP# 1907-70 | Bit Mill & Overlay, Guardrail, Drainage, BR Deck Repair | HI
SP# 1913-70 | Bit Mill & Overlay and Pedestrian ADA improvements | HI
SP# 1985-132 | Construct EB Wakota Bridge | MED
SP# 1985-140 | Thin Mill and Overlay | MED
SP# 2700-54 | Signal Timing and Intall Fiber Optics/Cameras @ Intersect | MED
SP# 2758-67 | Sign Replacement | MED
SP# 2773-03 | Lighting Replacement | MED
SP# 2775-18 | Replace Bridge Deck | HI
SP# 2780-69 | Lighting System Replacement | MED
SP# 2780-75 | Extent Ramp and Grade Separation | HI
SP# 2780-78 | Add Parallel Acceleration Ln | MED
SP# 2780-80 | Construct EB CD Rd for SB TH101 | MED
SP# 2780-88 | Bit Overlay | MED
SP# 2781-441 | Redeck Bridges | HI
SP# 6282-187 | Mill & Overlay, Drainage, Shoulder Recon, etc. | HI
SP# 6284-141 | Construct SB Aux Ln | HI
SP# 6285-142 | Ramp Modification, Bridge Widening | HI
SP# 8205-111 | Concrete Overlay | HI
SP# 8285-94 | Unbonded Conc Overlay & Conenct Existing Aux Lanes | HI
SP# 8286-64 | Unbonded 10" PCC Overlay, Guardrail, Pipes, Structures | HI

## 'Add Work Zone Config.'
Rote ID # | Memo | Start | End | Begin Station | End Station
SP# 0214-41 | No Lane Config Available | 2010-04-19 | 2010-09-13 | S958 | S962
SP# 0280-61 | No Lane Config Available | 2010-04-19 | 2010-09-30 | S659 | S1862
SP# 1907-70 | No Lane Config Available | 2010-04-16 | 2010-06-19 | S5212 | S5214
SP# 1913-70 | No Lane Config Available | 2010-07-06 | 2010-07-24 | S1597 | S1595
SP# 1985-132 | No Lane Config Available | 2008-04-15 | 2010-09-14 | S1020 | S1021
SP# 1985-140 | No Lane Config Available | 2010-07-26 | 2011-01-26 | S863 | S1201
SP# 2700-54 | No Lane Config Available | 2010-09-03 | 2011-03-03 | S269 | S291
SP# 2758-67 | No Lane Config Available | 2010-05-01 | 2010-07-30 | S522 | S531
SP# 2773-03 | No Lane Config Available | 2010-04-12 | 2010-05-28 | S304 | S313
SP# 2775-18 | No Lane Config Available | 2010-07-06 | 2010-11-01 | S322 | S322
SP# 2780-69 | No Lane Config Available | 2010-06-14 | 2010-09-24 | S1115 | S1115
SP# 2780-75 | No Lane Config Available | 2010-04-12 | 2010-10-29 | S1115 | S1115
SP# 2780-78 | No Lane Config Available | 2010-06-14 | 2010-09-24 | S1115 | S1117
SP# 2780-80 | No Lane Config Available | 2010-06-14 | 2010-09-24 | S1115 | S1115
SP# 2780-88 | No Lane Config Available | 2010-06-14 | 2010-09-24 | S1741 | S1117
SP# 2781-441 | No Lane Config Available | 2010-06-21 | 2011-09-01 | S557 | S557
SP# 6282-187 | No Lane Config Available | 2010-05-10 | 2010-08-20 | S468 | S1816
SP# 6284-141 | No Lane Config Available | 2010-04-19 | 2010-09-03 | S1861 | S670
SP# 6285-142 | No Lane Config Available | 2010-05-05 | 2010-09-05 | S184 | S203
SP# 8205-111 | No Lane Config Available | 2010-05-24 | 2010-10-01 | S1916 | S1931
SP# 8285-94 | No Lane Config Available | 2010-04-10 | 2010-08-27 | S1025 | S1026
SP# 8286-64 | No Lane Config Available | 2010-04-19 | 2010-10-01 | S1027 | S1418