## Add Work Zone
Name | Description | IMPACT
SP# 0202-94 | Mill & Overlay, Aggregate shoulder, drainage, etc. | MED
SP# 0285-65 | Mill & Overlay, CPR, Guardrail, Drainage, Bridge work | MI
SP# 1901-162 | Paint Bridges | HI
SP# 1982-148 | TH110 Signal Replacement | MED
SP# 1982-161 | Redeck, Repaint, and Deck Repair Bridges | HI
SP# 2750-75 | Convert 93rd intersection into Folded Diamond Half Int | MED
SP# 2750-80 | Conc Repair | MED
SP# 2755-90 | Redeck bridge, replace approach panels, signal interconnect | MED
SP# 2772-92 | Mill & Overlay, Crack & Seat old Conc, add Escape Ln, etc. | HI
SP# 2772-96 | Rehab Bridges, Storm Sewer Repair | HI
SP# 2776-103 | Replace Strip Seal Joints & Drain work on BRs, etc. | HI
SP# 2785-364 | Add WB Aux Ln, noisewall, drainage, ponding, lighting, etc. | HI
SP# 2785-367 | Mill & Overlay, Const. Aux Ln @ Portlabd Ave, etc. | HI
SP# 2789-131 | *no start/end, drawn from map* Electrical upgrades, etc. | MED
SP# 2789-133 | Modify CD Road and convert to individual exits | MED
SP# 6211-90 | Construct Interchange @ English Street | HI
SP# 6212-167 | Replace Bridge, Approaches, Guardrail, Storm Sewer & Ponds | HI
SP# 6283-174 | Repar/Replace Pipes, Structures, and Aprons | HI
SP# 6285-135 | Interchange Reconstruction | HI

## 'Add Work Zone Config.'
Rote ID # | Memo | Start | End | Begin Station | End Station
SP# 0202-94 | No Lane Config Available | 2013-05-15 | 2013-10-18 | S940 | S949
SP# 0285-65 | No Lane Config Available | 2013-06-03 | 2013-10-11 | S131 | S184
SP# 1901-162 | No Lane Config Available | 2013-04-26 | 2013-08-16 | S73 | S73
SP# 1982-148 | No Lane Config Available | 2012-07-20 | 2013-01-20 | S828 | S828
SP# 1982-161 | No Lane Config Available | 2013-04-26 | 2013-08-16 | S870 | S878
SP# 2750-75 | No Lane Config Available | 2013-04-01 | 2013-11-15 | S1800 | S1800
SP# 2750-80 | No Lane Config Available | 2013-04-01 | 2013-10-31 | S1802 | S1966
SP# 2755-90 | No Lane Config Available | 2013-04-26 | 2013-07-26 | S1614 | S1614
SP# 2772-92 | No Lane Config Available | 2013-05-31 | 2013-08-29 | S443 | S756
SP# 2772-96 | No Lane Config Available | 2013-06-03 | 2013-09-27 | S431 | S432
SP# 2776-103 | No Lane Config Available | 2013-06-28 | 2013-08-20 | S1611 | S1143
SP# 2785-364 | No Lane Config Available | 2012-07-23 | 2013-11-15 | S194 | S120
SP# 2785-367 | No Lane Config Available | 2012-07-23 | 2013-11-15 | S196 | S492
SP# 2789-131 | No Lane Config Available | 2013-05-15 | 2013-08-01 | S1964 | S290
SP# 2789-133 | No Lane Config Available | 2013-09-16 | 2013-10-25 | S269 | S269
SP# 6211-90 | No Lane Config Available | 2013-04-01 | 2013-12-07 | S1826 | S1827
SP# 6212-167 | No Lane Config Available | 2013-06-13 | 2013-10-15 | S602 | S603
SP# 6283-174 | No Lane Config Available | 2013-08-27 | 2013-09-27 | S1042 | S1045
SP# 6285-135 | No Lane Config Available | 2011-09-11 | 2013-11-01 | S1075 | S1076